## Start here
Exercise 4-6: Monthly Cost Variance, participant worksheet
Training sample. All names and figures are fabricated. Yellow cells are for you to fill in.
Step | Where | What to do
1 | Guide, Prompt 1 | Paste Siti's email into Copilot Chat with Prompt 1. Write what she needs, the exact flag rule and your quality requirements on the "My notes" tab, section A.
2 | Tab: October 2026 | Click into B12, C12 and E5 and read the formula bar. Record what you find on "My notes", section B. Do not change anything yet.
3 | Guide, Prompt 2 | Build your critical prompt (RCTF+C) asking for formulas, not numbers. Put the formulas into row 5 of the "October 2026" tab and fill down to row 11. Fix the Actual total.
4 | Tab: Hand check | Test one row by hand, then check every flag against Siti's rule. Record your results on the "Hand check" tab.
5 | Guide, Prompt 3 | Ask AI to explain Amir's forecast formula. Record what you found, and what you would tell Siti, on "My notes", section C.
6 | My notes, section D | Tick the final checklist.
Tips
- | Ask for the method, not the result: you want formulas that work every month.
- | AI cannot see your sheet unless Copilot is working inside it, so describe where everything is.
- | The "October 2026" tab is the inherited workbook. Keep a copy of the original before you change it (File, Save As).

## October 2026
Site cost report
Reporting month: October 2026 ¦ Training sample, all figures fabricated
Category | Budget (Oct, RM) | Actual (Oct, RM) | Actual YTD (Jan to Oct, RM) | Full-year forecast (RM)
Fuel | 42000 | 45500 | 418000
Manpower | 128000 | 124200 | 1262000
Catering | 36500 | 38900 | 371500
Maintenance | 19000 | 21300 | 196400
Transport | 24000 | 25100 | 243800
Accommodation utilities | 8500 | 9600 | 88300
Communications | 3000 | 5400 | 33600
Total |  | 271000
Working area: add your new columns (F onwards) in row 4 and fill down to row 11. Fix the Actual total in C12.

## My notes
My notes
Fill in the yellow cells as you go. Nothing here is sent anywhere.
A. Understand the request (Step 1)
Item | My answer
What Siti needs, for each cost line
The exact flag rule, word for word
My quality requirements for the report
B. Look inside the workbook (Step 2)
Cell | Formula or typed number? | Anything that worries you?
B12 (Budget total)
C12 (Actual total)
E5 (Fuel forecast)
C. Inherited forecast formula (Step 4)
Question | My answer
What does the formula in E5 do, in plain English?
Is the current forecast too high, too low or right? By roughly how much?
What would have to change every month to keep it right?
What I would tell Siti
D. Check your work (Step 5)
I can honestly say yes to... | Done?
I checked which cells were formulas and which were typed, before changing anything.
I asked for formulas, not numbers.
I tested at least one row by hand, and Excel agreed.
Every flag matches Siti's rule, with both conditions.
No total in the report is a typed number.
I understand the inherited forecast formula and what is wrong with it.
The report would work next month without anyone retyping numbers.
Ticked fewer than five? Go back to the checks under Prompt 2.

## Hand check
Hand check
Work these out with a calculator, not with Excel or AI. Then compare with your formulas on the October 2026 tab.
1. Test one row by hand
Row I chose | Variance by hand (RM) | Variance % by hand | Excel variance | Excel variance % | Do they match?
2. Check every flag against the rule
Write the rule in your own words:
Category | Variance by hand (RM) | Variance % by hand | Condition 1 met? | Condition 2 met? | Should it be flagged? | Flag in my Excel | Match?
Fuel
Manpower
Catering
Maintenance
Transport
Accommodation utilities
Communications
Number of lines flagged
3. Stretch question
Would your formula still flag Manpower if it were 6% under budget (and still more than RM 2,000 away)? How do you know?